## LP Planning Committee Goals - L
Legacy Park Planning Committee Goals
Goal | Project | Additional Steps | FYQ | Board/Committee Roles/Notes
I. Improvements to Lake and Conservation Area (Opportunity to implement environmental, educational and recreational components of the plan to enhance public use of the property, improve the environmental conditions and expand on the work of partners and volunteers already working in the area): | I-A. Partner with City of Decatur and Environmental Sustainability Board to issue RFP and implement phase 1 of Invasive Plant Removal Program. | I-A1. Issue RFP | CY 2021 Q1 | Funds are available. RFP is a City function.
|  | I-A2. Secure contract with invasive removal team | CY 2021 Q2 | board input to the City on contractor selection.
|  | I-A3. Schedule Community Volunteer Days | CY 2021 Q3 | Event occurs in Q3
| I-B. Install appropriate signage, fencing and gates to restrict vehicular access to meadows and conservation area (propose fencing and gates that reflect farming history of the area with fencing spaced to allow multiple pedestrian access points) | I-B1. Install signage restricting vehicle access in accordance with city ordinances to allow for enforcement as necessary | CY 2021 Q1 | Mostly complete. A few additional signs need to be installed.
|  | I-B2. Issue bids for fencing and gate installations | CY 2021 Q1 | Committee to provide input on gate/fencing designs
|  | I-B3. Contract for purchase of gravel for northern most drive up to the barn, creation of small gravel two parking spaces for Global Growers Garden and install gate to limit vehicular access beyond the barn to maintenance vehicles) | CY 2021 Q1 CY 2021 Q2 | Q1 - Issue RFP Q2 - Select contractor Explore ordering a larger load of gravel with the City
| I-C. Issue RFP for environmental education partner | I-C1. Complete RFP for program partnership, review and select program partner | CY 2021 Q2 CY 2021 Q3 | Q2 - RFP Q3 - Select Contractor (Board approves)
|  | I-C2. Provide limited office space and storage space for partner | CY 2021 Q2 or Q3
|  | I-C3. Develop educational signage program with partner for conservation area & lake | CY 2022 Q1 or Q2
|  | I-C4. Engage with partner for the future renovation of the Barn to provide programming and office space in exchange for shared renovation costs | CY 2022 Q3 or Q4 | Board approves shared costs agreement
| I-D. Partner with City of Decatur and ESB to conduct engineering study to replace dam assist with fundraising for implementation funding |  | In progress | Board involved in decision making process
II. Barn Stabilization (Preserve and adaptive reuse of last remaining element of farming history at the site; support the development of environmental education, public access and activity in the conservation area; potential for rental income generation) | II-A. Contract with design professionals to complete structural analysis and develop concept plans for barn renovation; code analysis; and specifications for stabilization and engineering necessary to complete stabilization by June 30, 2021 and provide cost estimates for renovation phase |  | In progress | Funding secured; Proposal from engineering firm to bid out the stabilization work. Part of the proposal includes design concepts, so that we will understand costs for renovation.
| II-B. Bid out engineering and stabilization work for current city fiscal year |  | CY 2021 Q2
| II-C. Submit capital budget request for renovation costs |  | CY 2021 Q1 | Capital request reviewed and approved by Finance Committee & Board
| II-D. Initiate fundraising strategy as needed in partnership with Environment Education Partner |  | CY 2021 Q4
III. Renovate and Repurpose Existing Buildings (Adaptive reuse opportunity to preserve historic buildings and create a model for creative, alternative approaches to affordable housing like the growing co-housing movement to invest and manage the properties) | III-A. Complete ADA Access Plan for Chapel and Dining Hall to submit budget request to City of Decatur (Ramp design and cost estimates complete by January 30, 2021 |  | In progress | A not to exceed estimate has been provided.
| III-B. Complete Dining Hall Renovation currently included in City Capital budget (construction bidding in process) |  | In progress | Design Completed Public Works Dept drafting the RFP
| III-C. Issue an RFP for creative, alternative affordable housing management for Glenn and Sam Bell. |  | CY 2021 Q3 | Committee to review most competitive RFPs. Board to take a recommendation to the City Commission.
| III-D. Issue an RFP for the management of affordable housing and studio space for artists at the four cottages identified as the “Creative Village” considering co-housing managements companies and partnership teams between housing managers and arts organizations. |  | CY 2021 Q4 | Committee to review most competitive RFPs. Board to take a recommendation to the City Commission.
| III-E. Issue an RFP for Williams Cottage |  | CY 2021 Q3 | Committee to review most competitive RFPs. Board to take a recommendation to the City Commission.
| III-F. Identify potential uses and priorities for Education Center/Infirmary; Whitehead; and Leigh Cottage - potential CBO space |  | CY 2021 Q4 | Committee to review most competitive RFPs. Board to take a recommendation to the City Commission.
| III-G. Partner with the City of Decatur to create and issue a RFP for the north village affordable housing cottage development |  | CY 2021 Q4 | Board provides input to City of Decatur
IV. Picnic Area and Front Lawn Renovation (Improve maintenance and appearance of front lawn and planting beds and purchase outdoor furniture for area around central building to create a more attractive, inviting and well-cared for image) | IV-A. Contact current city landscape contractor to develop a plan and pricing for front lawn fertilization and improvement program and pricing as an add on to existing contract |  | In progress
| IV-B. Work with current landscape contractor to create a planting plan for front entrance signs and front and rear planting areas of the Administration building |  | In progress
| IV-C. Coordinate with the master gardeners and local volunteers for a one-day pruning, invasive plant removal and mulching of existing large azalea beds in central campus area |  | In progress
| IV-D. Purchase new picnic tables and trash cans for the area to the south of the dining hall |  | In progress
| IV-E. Remove all rotted picnic tables from the property and salvage those still useable to create several picnic table groupings around creative village area, playing fields, meadow and southern-most playground areas |  | In progress
| IV-F. Install dog poop bag stations at strategic locations around the property and add additional signage related to cleaning up after dogs |  | In progress | Priority
| IV-G. Complete design and installation of temporary visioning signs and directional signage currently budgeted |  | In progress
V. Provide support to the City of Decatur and Community Partners as needed to pursue opportunities to implement components of the Legacy Park Master Plan |  |  | Ongoing